## Index
Sources
Project Challenge by Thinking Tools
Section Links
Definitions
Scope
Standards & Procedures
Acceptance Procedures
Project Organization
Roles & Responsibilities
Deliveries
Change Request Log

## Definitions
Back to Index
Stages | Description
Concept Definition | Define the scope of the nw system by defining the high level system requirements and developing the conceptual design of the applications
Function Definition | Define the data requirements and information processing requirements of the new system and specify a data model and system functions that meet the detailed requirements. Develop plans for subsequent sysem deployment, site preparation, system test, acceptance test and training.
Structural Design | Depsign the application software and its integration with the technology architecture. Test procedutes(test data and expected results) for the various testing layers(e.g., system test and acceptance test) are also developed.
Development | Develop the application software and its integration with the systm infrastructure. Also, prepare user aids and training materials, prepare a software deployment plan, and fully test the system.
Deployment | Release the working system to the production sites. Specific objectives include installation of the application software and conversion data, and training of the customner staff.
Stage | Item | Definition
Concept Definition | Requirements Definition deliverable | A document that defines the relevant opetational, performance, application and architectural requirements of the system
Concept Definition | Conceptual Architecture Definition deliverable | A document that defines the chosen application and technology profiles based upon the requirements.
Concept Definition | Technology Proof of Concept deliverable | A set of informal documents consisting of tests and trials used to validate performance of chosen products against requirements.
Concept Definition | System Blueprint deliverable | A document that provides a complete description of the technology architecture, showing how the components are integrated.
Function Definition | Functional Design Specification deliverable | A document that specifies the business processes to be performed by the system.
Function Definition | Prototype deliverable | This deliverable demonstrates the look, feel and flow of the user intergace(horizontal) and simulates the core functionality of the system(vertical).
Function Definition | Training Plan deliverable | A plan which details how customer staff, who will use or support the system, will be trained.
Function Definition | Facility Requirements deliverable | A document that defines the preliminary facility requirements to further refine implementation practicalitites.
Structural Design | Structural Design Specification deliverable | A document that defines a structural framework for the physical components.
Structural Design | Conversion Design deliverable | A document that provides a design specification for the coversion system.
Structural Design | Application User Aids deliverable | Instructional material for the customer user community that describes how to use the system functions and features.
Structural Design | Site Readiness deliverable | A milestone which indicates copletion of site preparation and sign-off that the site is ready for installation.
Structural Design | Technology Procured deliverable | A milestone which indicates that technology components are ordered and preparation for staging is complete.
Development | Detailed Design Specification deliverable | A document provides a detailed specification for the program units ientified in the Structural Design Specification.
Development | Application Software deliverable | Developed program units.
Development | Conversion Software deliverable | Software developed from the conversion esign specification.
Development | System Guide deliverable | Instructional information, such as a system overview and maintenance procedures, for the customer staff who will maintain the new system(maintenance), and information for the customer staff who will support the system that describes the operation of the system and provides instructions for running batch jobs and distributing output(operations).
Deployment | Site Technology Installation deliverable | A milestone which indicates completed site development, including all components installed and signed-off, and support procedures initiated.
Deployment | Production System deliverable | A milestone which indicates that the application system has been installed, configured and tested, and warranty support has been provided.

## Scope
Back to Index

## Standards&Procedures
Back to Index

## AcceptanceProcedures
Back to Index

## ProjectOrg
Back to Index

## Roles&Responsblty
Back to Index

## Deliver
Back to Index |  |  |  |  | Effort Days
Stage | Deliverable | Date Submitted | Status | Status Date | Budget: 706 | Actual: 826 | Diff: -120
Concept Definition | Functional Design Specification | 1996-11-06 | Accepted | 1996-11-07 | 305 | 353 | -48
Concept Definition | Prototype | 1996-12-17 | Accepted | 1996-12-18 | 231 | 279 | -48
Concept Definition | Training Plan | 1996-11-13 | Accepted | 1996-11-18 | 40 | 40 | 0
Concept Definition | Facility Requirements | 1996-11-27 | Accepted | 1996-12-02 | 20 | 20 | 0
Concept Definition | Acceptance Test Specification | 1996-12-27 | Submitted |  | 110 | 134 | -24
Concept Definition | Facility Deployment

## CR
Back to Index | Change Request Log
CR# | Cost | Effort Days | Effect on Project Schedule | Date Submitted | Status | Status Date
1 | 13500 | 12 | 0 | 1996-12-18 | Rejected | 1996-12-20
2 | 0 | 25 | 0 | 1996-12-18 | Accepted | 1996-12-19
3 | 2000 | 0 | 0 | 1996-12-20 | Submitted